## Sheet1
|  | Owner | Sat | Sun | Mon | Tue | Wed | Thu
- Home (Restaurant introduction) |  | But | Start | HTML | Code | Code | Merge and check | Presentation
- Display menu (list all dishes by category) |  | Lam | Start | HTML | Code | Code | Merge and check | Presentation
- Display detail of the dish (ingredients, price,…) |  | Lam | Start | HTML | Code | Code | Merge and check | Presentation
| + Add order | Lam | Start | HTML | Code | Code | Merge and check | Presentation
| + Allow users to post reviews on that dish. | Lam | Start | HTML | Code | Code | Merge and check | Presentation
- Order (COD only) |  | Huan | Start | HTML | Code | Code | Merge and check | Presentation
| + View/edit/delete order | Huan | Start | HTML | Code | Code | Merge and check | Presentation
| + Input shipment information | Huan | Start | HTML | Code | Code | Merge and check | Presentation
| + Complete | Huan | Start | HTML | Code | Code | Merge and check | Presentation
- Reservation |  | But | Start | HTML | Code | Code | Merge and check | Presentation
| Setup project | But | Start | Finish
| Design database | But | Start | Finish
| Setup database | But | Start | Finish